## Project Data
Project Name | ...
Online team meeting | https://tu-berlin.zoom-x.de/j/64327398600?pwd=iKF2e9D7PEM8Q552cgabakS0O6L9xa.1
Production system (if any) | http://amos.b-iq.net/
Test system (if any) | ...
GitHub repository | https://github.com/amosproj/amos2025ss02-building-documentation-management-system
GitHub feature board | https://github.com/orgs/amosproj/projects/80/views/2
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/84
Team T-shirt (white) | https://www.shirtinator.de/loadBasket/vNV5XYUVMtq
Team T-shirt (black) | https://www.shirtinator.de/loadBasket/nQ9JYKa8F3W
Additional materials | ...
Team maling list | oss-amos-proj2@lists.fau.de

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Kurtz | Daniel | daku-de | daniel.kurtz@fau.de
Deli | Deniz | ddeli | d.deli@campus.tu-berlin.de
Egge | Carl | carl-egge | c.egge@campus.tu-berlin.de
Halder | Arpita | arpita739 | arpita.halder@fau.de
Kazi | Masudur Rahaman | kamsur | masudur.r.kazi@fau.de
Almalla | Nirmin | Nirmin96 | nirmin.almalla@campus.tu-berlin.de
Ouabo | Samuel | so77nava | samuel.ouabo@fau.de
Billah | Masum | masum-abid | masum.billah@fau.de
Hussain | Syed Affan | syedaffan10 | affan.hussain@fau.de
Djamen | Bastiane | bastydjamen | eugenie.djamen@fau.de

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | Comment
1 | 2025-04-16 |  | Daniel | Everyone else | N/A | Deniz
2 | 2025-04-23 | Daniel | Carl | Everyone else | Arpita | Deniz
3 | 2025-04-30 | Carl | Daniel | Everyone else | Masudur Rahaman | Deniz
4 | 2025-05-07 | Daniel | Carl | Everyone else | Samuel | Deniz
5 | 2025-05-14 | Carl | Daniel | Everyone else | Masum | Deniz
6 | 2025-05-21 | Daniel | Carl | Everyone else | Syed Affan | Deniz
7 | 2025-05-28 | Carl | Daniel | Everyone else | Bastiane | Deniz | Mid-term due
8 | 2025-06-04 | Daniel | Carl | Everyone else | Arpita | Deniz
9 | 2025-06-11 | Carl | Daniel | Everyone else | Masudur Rahaman | Deniz
10 | 2025-06-18 | Daniel | Carl | Everyone else | Samuel | Deniz
11 | 2025-06-25 | Carl | Daniel | Everyone else | Masum | Deniz
12 | 2025-07-02 | Daniel | Carl | Everyone else | Syed Affan | Deniz
13 | 2025-07-09 | Carl | Daniel | Everyone else | Bastiane | Deniz
14 | 2025-07-16 | Daniel | Carl | Everyone else | Arpita | Deniz | Demo day!
15 | 2025-07-23 | Carl | Daniel | Everyone else | Masudur Rahaman | Deniz | Retrospective
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here
Formulas:
Meeting Day = [Meeting Day, row above]+7

## Team Contract
Goals | Deliver a product that meets the stakeholder requirements.
Everybody in the team wants to gain some new knowledge.
Every team member should have fun during the project.
Coming up with innovative solutions using modern technology.
Develop our skills in teamwork and communication.
Meeting norms | We meet every Wednesday in the team meeting.
POs will have weekly meetings with the stakeholder which are optional for the SDs.
Everybody should be on time for the team meeting. If you are late or unavailable please inform the group beforehand through the defined communication channels.
We practice a respectful and non-disciminative communication with all team members.
Everyone should do their best to participate with Camera and Microphone turned on in the team meetings.
Meetings will follow a clear structure that is quickly presented at the beginning of the meeting.
Working norms | We communicate or problems with the group and help colleagues that are stuck.
We will follow a common Git Flow that will be defined by the SDs and follows industry best-practices.
Commit often and use clear commit messages to avoid unnecessary conflicts.
We will always use pull requests and code reviews instead of force pushes to improve coding quality.
Coordination norms | The POs are responsible for allocating assignments.
The POs will alternatingly moderate the team meetings. The SM is responsible for keeping the team meetings on track.
Communication norms | We will use Discord as technical channel for programming topics.
The Email list and Stand Up Email will be for organizational communication and announcements.
Everybody should check these channels daily.
We use english as a working language.
The WhatsApp group is an additional optional channel for group conversations.
Consideration norms | No side conversation and technical conversations during the team meeting.
For team decisions and disagreements an anonymous vote will be held and the majority decides.
Cont. improvement norms | Stand Up Emails and Hapiness Index will be used to track team work.
No pull requests should be accepted without feedback from at least one other team member (Positive feedback is welcome).
We practice open feedback culture and continously improve our working environment.
Rewards | By delivering on time everyone can reward themself with a free weekend.
Sanctions | We define no sanctions.
Signatures
Scrum Master | Deniz Deli
Product owner | Daniel Kurtz
Product owner | Carl Egge
Software developer | Masudur Rahaman Kazi
Software developer | Bastiane Djamen
Software developer | Nirmin Almalla
Software developer | Arpita Halder
Software developer | Syed Affan Hussain
Software developer | Masum Billah
Software developer | Samuel Ouabo

## Product Goal
Product Vision | Project Mission
Managing building portfolios often means navigating scattered, inconsistent document repositories. Our system enables facility managers to easily upload files, automatically extract and validate critical metadata, classify documents by type and building, and find exactly what they need through intuitive search and natural-language queries — reducing search times from hours to seconds. By integrating into broader building document management platforms, our solution enhances existing workflows and ensures seamless access to critical information across systems. | We aim to build a secure, multi-tenant backend that stores uploaded permits, certificates, and maintenance reports; applies AI-driven OCR and metadata extraction to classify and validate each document; and provides a web UI where users can query and filter their building records using plain language. By implementing and demonstrating a full workflow — from document upload to automatic processing and natural-language search on sample data — we will create the technical foundation for a production-ready system that significantly reduces the time and effort required to manage building documents.

## Product Glossary
Term | Definition
Document | A term to describe arbritrary files that contain information about a Building (e.g. Energieausweis, floor plan, ...)
Building | Corresponds to a real world building object and is described by one ore more Documents
Organization | An Organization is a high level data entity that is responsible for building one or more buildings and managing the corresponding data
User | A system user that belongs to one organization and interacts with the Document data
OpenAPI Client | Tool that handles interactions with APIs defined by OpenAPI specifications
File Explorer | Interface to browse Documents
Ollama | Tool for running LLMs locally or on premise
JWT | JSON Web Token used for secure user authentication
Chatbot | Interface to communicate with LLM
Energieausweis | Energy certificate showing a building’s energy efficiency
Document Meta Data | Information about Document files including knowledge that has been extracted from the Documents content

## Sprint Goals
Sprint # | Sprint goal
1 | Get to know the team and understand the stakeholder's requirements
2 | Start scaffolding basic backend and frontend infrastructure and research domain-specific knowledge
3 | Set up unified development and production environment through containerization and tooling
4 | Fix the issue of sensitive documents in the repository and enhance backend with endpoints and database connection
5 | Extend and prepare components so they can be easily connected
6 | Prepare mid-project release by binding frontend and backend together and finalizing container orchestration
7 | Refactor and enhance frontend to improve application data flow
8
9
10
11
12
13
14
15

## Velocity Tracking
Sprint # | Story Points Realized | Average
1 | 3 | 22.2
2 | 15 | 22.2
3 | 24 | 22.2
4 | 51 | 22.2
5 | 18 | 22.2
6 |  | 22.2
7 |  | 22.2
8 |  | 22.2
9 |  | 22.2
10 |  | 22.2
11 |  | 22.2
12 |  | 22.2
13 |  | 22.2
14 |  | 22.2
15 |  | 22.2

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 143 | 143 | 111 | 111
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 | Get to know the team and understand the stakeholder's requirements |  | 3 | 143 | 3 | 143
2 | Start scaffolding basic backend and frontend infrastructure and research domain-specific knowledge |  | 16 | 140 | 15 | 140
3 | Set up unified development and production environment through containerization and tooling |  | 16 | 124 | 24 | 125
4 | Fix the issue of sensitive documents in the repository and enhance backend with endpoints and database connection |  | 43 | 108 | 51 | 101
5 | Extend and prepare components so they can be easily connected |  | 49 | 65 | 18 | 50
6 | Prepare mid-project release by binding frontend and backend together and finalizing container orchestration |  | 16 | 16 | 0 | 32
Features
1 | Get to know the team and understand the stakeholder's requirements
|  | Align on Development Guidelines | 1 |  | 1
|  | Meet the industry partner | 1 |  | 1
|  | Create a team logo | 1 |  | 1
2 | Start scaffolding basic backend and frontend infrastructure and research domain-specific knowledge
|  | Create a shirt design | 1 |  | 1
|  | Initialize SW Bill of Materials | 2 |  | 2
|  | Create SW Architecture Description | 3 |  | 3
|  | Scaffold Basic C# Web API | 3 |  | 2
|  | Scaffold Basic Angular Application | 3 |  | 3
|  | Research Local RAG-Based LLM Solutions | 2 |  | 2
|  | Research typical Building Documents | 2 |  | 2
3 | Set up unified development and production environment through containerization and tooling
|  | Dockerize Front-End | 2 |  | 3
|  | Dockerize Back-End | 2 |  | 2
|  | Create DB Scheme Diagram | 2 |  | 2
|  | Create README | 1 |  | 1
|  | Consolidate Project Structure | 2 |  | 2
|  | Create Docker-Compose File | 2 |  | 3
|  | Linting and Formatting Frontend | 1 |  | 1
|  | Linting and Formatting Backend | 1 |  | 2
|  | Set Up GitHub Actions Pipeline | 3 |  | 8
4 | Fix the issue of sensitive documents in the repository and enhance backend with endpoints and database connection
|  | Fix: Remove Sensitive Building Documents | 5 |  | 5
|  | Implement Backend CRUD for Document | 8 |  | 8
|  | Implement Backend CRUD for Building | 5 |  | 8
|  | Integrate Linting into Pipeline | 5 |  | 8
|  | Add Authentication to Frontend | 3 |  | 5
|  | Design Frontend Mockup | 5 |  | 8
|  | Set Up Ollama | 3 |  | 3
|  | Implement Basic DB models in C# | 8 |  | 5
|  | Reorganize DB Scheme | 1 |  | 1
5 | Extend and prepare components so they can be easily connected
|  | Document Build Process in Video Format | 2 |  | 5
|  | Support OpenAPI Client Generation | 8
|  | Persist Data Using Docker Volumes | 8
|  | Enhance Angular Frontend based on Mock Up | 5
|  | Persist Building Data in DB | 5 |  | 5
|  | Query Ollama via Backend | 5 |  | 5
|  | Agree on DoD | 3 |  | 3
|  | Set Up Apache Tika | 5
|  | Add Organization Entity to DB | 8
6 | Prepare mid-project release by binding frontend and backend together and finalizing container orchestration
|  | Replace Default Web Services with Angular Frontend | 1
|  | Upload and Store Document via Frontend | 3
|  | Document View Page displays Actual Documents | 3
|  | Display Stored Documents in the Document Explorer | 3
|  | Connect Frontend to LLM | 3
|  | Update Bill of Materials | 1
|  | Adopt Feature Branch Workflow and Clean Up Branches | 2

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 0 | 0
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
... |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done
1 | Documentation is updated to include the new feature | Atleast one error-free functionality (which has passed feature DoD), more than previous release. | Stakeholders have reviewed and signed off the release
2 | Another SD, not the implementer, has reviewed the feature using the documentation. | Entire project builds and deploys to production. | Documentation (user + technical) is complete and comprehensive
3 | GitHub actions workflows for linting pass | Non-UI logic (e.g., DB transactions) verified by an SD or RM. | No critical open issues remain in backlog
4 | Feature branch has been merged and deleted | Release manager writes release notes (& Change log)
5 |  | All GitHub actions workflows pass
6 |  | Bill of Materials is up to date

## Documentation
Type | Link / reference
User Documentation | https://github.com/amosproj/amos2025ss02-building-documentation-management-system/wiki/User-Documentation
Build and Deploy Documentation | https://github.com/amosproj/amos2025ss02-building-documentation-management-system/wiki/Build-&-Deploy
Technical Documentation | https://github.com/amosproj/amos2025ss02-building-documentation-management-system/wiki/Technical-Design

## Bill of Materials
# | Context | Name | Version | License | Comment
1 | UI | Angular | 19 | MIT License | Needed for developing UI as per client requirement
2 | UI | Node.js | 22.15.0 | Custom (open-source) | Needed for Angular
3 | UI | npm | 10.9.2 | Artistic License 2.0 with additions | Package manager, needed for Angular
4 | Backend (Framework) | Microsoft.NETCore.App | Implicit | MIT License | .NET Core base runtime (System., Microsoft.)
5 | Backend (Framework) | Microsoft.ASPNetCore.App | Implicit | MIT License | ASP.NET Core web framework (Controllers, Routing, Authorization)
6 | Backend (Library) | Swashbuckle.AspNetCore | 6.5.0 | MIT License | Provides Swagger/OpenAPI documentation and UI
7 | Backend (Library) | AspNetCore.HealthChecks.UI | 6.0.4 | Apache 2.0 License | Adds health check endpoints (/healthz) and optional health UI
8 | Backend (Framework) | Entity Framework Core .NET Command-Line Tools | 9.0.4 | Apache 2.0 License | Used to manage EF Core database tasks from the terminal

## Planning Poker
Last Name | First Name | Value
Halder | Arpita | 1 | 1 | OK
Kazi | Masudur Rahaman | 1
Ouabo | Samuel | 1
Billah | Masum | 1
Hussain | Syed Affan | 1 | 0 | No size
Djamen | Bastiane | 1 | 1 | Trivial size
|  |  | 2 | Small size
|  |  | 3 | Medium size
|  |  | 5 | Large size
|  |  | 8 | Very large size
|  |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value